## README
Pravah: component and Google service map
Companion to docs/SPEC.md (build specification v1.0, 14 Oct 2026). Stage IDs (S0–S19) match the spec.
How to use
1. Components: one row per stage / component / logic piece, with the Google service it uses. Build top to bottom.
2. Only edit the yellow 'Status' column (dropdown: Not started, In progress, Done, Blocked). Progress updates automatically.
3. Google services: every Google service the platform uses and what it is for.
4. Data sources: every dataset with its access ID, licence and whether its ID was verified on 14 Oct 2026.
5. Compliance: challenge rules and Google Maps Platform terms, and how the design complies.
6. Day plan and Progress: schedule and live completion by stage.
Rules this sheet enforces
• AI = Gemini only (Vertex AI, ADK). Hosting = Cloud Run + Firebase Hosting. Data/compute/storage = Google Cloud.
• Non-Google items are open-source libraries or open data (mainly OpenStreetMap). Each is flagged in the 'Non-Google element' column with its reason.
• Google Maps Platform is used for display, forecasts and geocoding only. Its content is never used as analysis input (Maps terms §3.2.3).
Example row (Components)
C27 ¦ S3 ¦ Rational method runoff ¦ Q = 0.278·C·i·A ¦ C (Dynamic World), rain mm/h, A_local km² ¦ Q per reach per hour ¦ Cloud Run (compute) ¦ engine code; inputs from Earth Engine ¦ — ¦ — ¦ Compliant ¦ N/A ¦ P0 ¦ Thu 15 ¦ C26, C21 ¦ Not started

## Components
ID | Stage | Component | Logic / method | Inputs | Outputs | Google service(s) | Specific API / dataset / product | Non-Google element | Why allowed | Challenge-rule check | Maps ToS check | Priority | Build day | Depends on | Status
C01 | S0 | Backend hosting | FastAPI app in a container; --no-cpu-throttling, 4 GiB, 900 s timeout | Code | Public HTTPS API | Cloud Run; Cloud Build; Artifact Registry | Cloud Run service pravah-backend (asia-south1) | FastAPI (open-source) | Library, not a model or host | Compliant (required host) | N/A | P0 | Wed 14 | — | Not started
C02 | S0 | Frontend hosting | Static React build; /api/** rewrite to Cloud Run | Built frontend | Public web app | Firebase Hosting | firebase.json rewrite → run.serviceId | React, Vite (open-source) | Libraries | Compliant (required host) | N/A | P0 | Wed 14 | C01 | Not started
C03 | S0 | Keys and secrets | Browser key (referrer-restricted), server key (API-restricted) in Secret Manager | — | Restricted keys | Secret Manager; API Keys; IAM | maps-server-key secret; service account pravah-backend | — | — | Compliant | Keys restricted per Maps best practice | P0 | Wed 14 | — | Not started
C04 | S0 | Budget guardrail | Budget $100 with 25/50/75/100% alerts | — | Email alerts | Cloud Billing | Budgets & alerts | — | — | Compliant | N/A | P0 | Wed 14 | — | Not started
C05 | S0 | Model selection | List available models, human picks Fast and Pro | — | GEMINI_MODEL_FAST / _PRO env vars | Vertex AI | google-genai client.models.list() | — | — | Compliant (Gemini) | N/A | P0 | Wed 14 | C01 | Not started
C06 | S1 | AOI capture and validation | sha1 id, size limits (river ≤15 km, urban ≤4 km) | Drawn bbox | AOI doc | Firestore; Cloud Run | aois/{aoi_id} | — | — | Compliant | N/A | P0 | Wed 14 | C01 | Not started
C07 | S1 | Analysis grid (UTM, 30 m) | GridSpec, transforms, 4-corner overlay bounds | AOI bbox | GridSpec | Cloud Run (compute) | engines/grid.py | pyproj (open-source) | Library | Compliant | N/A | P0 | Wed 14 | C06 | Not started
C08 | S1 | Terrain: DEM, slope, aspect, curvature | computePixels to the grid; NumPy derivatives | AOI grid | dem, slope_deg, aspect_deg, curv | Earth Engine (noncommercial) | Copernicus DEM GLO-30 (COPERNICUS/DEM/GLO30 deprecated → successor GLO30_2024_1, VERIFY) | NumPy | Library | Compliant | Not Maps content (Elevation API deliberately NOT used, §3.2.3(c)(iii)) | P0 | Wed 14 | C07 | Not started
C09 | S1 | Hydrology layers: HAND, D8, upstream area | computePixels; bilinear for hnd/elv, nearest for dir/upa | AOI grid | hand, d8, upa, elv_hydro | Earth Engine (noncommercial) | MERIT/Hydro/v1_0_1 (hnd, dir, upa, elv) | — | — | Compliant | N/A | P0 | Wed 14 | C07 | Not started
C10 | S1 | Land cover | Mode of last 12 months of labels | AOI | lc_class (0–8) | Earth Engine (noncommercial) | GOOGLE/DYNAMICWORLD/V1 label | — | — | Compliant | N/A | P0 | Wed 14 | C07 | Not started
C11 | S1 | Vegetation (NDVI) | Dry-season median, cloud < 20% | AOI | ndvi | Earth Engine (noncommercial) | COPERNICUS/S2_SR_HARMONIZED B8/B4 | — | — | Compliant | N/A | P1 | Wed 14 | C07 | Not started
C12 | S1 | Soil clay | Surface clay fraction | AOI | soil_clay | Earth Engine (noncommercial) | OpenLandMap clay fraction (VERIFY ID/band) | — | — | Compliant | N/A | P1 | Wed 14 | C07 | Not started
C13 | S1 | Rainfall climatology | Mean of annual max daily rain 2001–2024 | AOI | rain_clim (mm/d) | Earth Engine (noncommercial) | UCSB-CHG/CHIRPS/DAILY precipitation | — | — | Compliant | N/A | P1 | Wed 14 | C07 | Not started
C14 | S1 | Historical flood grids | Sum of flood events; surface water occurrence | AOI | gfd_count, gsw_occ | Earth Engine (noncommercial) | GLOBAL_FLOOD_DB/MODIS_EVENTS/V1; JRC Global Surface Water (VERIFY version) | — | — | Compliant | N/A | P1 | Wed 14 | C07 | Not started
C15 | S1 | Population grid | Density at native res × 900 m²; rescaled to EE total | AOI | pop30 | Earth Engine (noncommercial) | WorldPop/GP/100m/pop (IND, latest year VERIFY) | — | — | Compliant | N/A | P0 | Wed 14 | C07 | Not started
C16 | S1 | Building footprints and heights | filterBounds + reduceRegions for height & presence 2016/2023 | AOI | buildings.parquet | Earth Engine (noncommercial) | GOOGLE/Research/open-buildings/v3/polygons; GOOGLE/Research/open-buildings-temporal/v1 | GeoPandas | Library | Compliant | N/A (not traced from Maps imagery, §3.2.3(c)(i) respected) | P0 | Wed 14 | C07 | Not started
C17 | S1 | Roads, POIs, waterways | OSMnx graphs (walk/drive), features_from_bbox | AOI + 3 km buffer | GraphML, pois.parquet, waterways.parquet | Cloud Storage (cache) | — | OpenStreetMap data via OSMnx/Overpass | Open data (ODbL); no Google road graph can legally be used for analysis | Compliant (open data) | Avoids Maps Roads/Places extraction (§3.2.3(a),(c)(iv)) | P0 | Wed 14 | C06 | Not started
C18 | S1 | Layer cache and status | Idempotent prepare_area; .npz per group | Layers | GCS objects; status doc | Cloud Storage; Firestore | gs://pravah-dss-data/aoi/{id}/… | — | — | Compliant | N/A | P0 | Wed 14 | C08–C17 | Not started
C19 | S1 | Overlay rendering | Raster → RGBA PNG; signed URLs; 4-corner bounds | Grids | PNG URLs | Cloud Storage | V4 signed URLs (24 h) | Pillow | Library | Compliant | Our own data drawn over Maps (allowed) | P0 | Wed 14 | C18 | Not started
C20 | S2 | Native hydro grid and D8 decode | EPSG:4326 3″ grid; D8 offsets; downstream index | MERIT dir | downstream[] | Earth Engine (noncommercial) | MERIT/Hydro/v1_0_1 (native grid) | NumPy | Library | Compliant | N/A | P0 | Wed 14 | C09 | Not started
C21 | S2 | Local contributing area | Kahn topological accumulation inside the grid | downstream | A_local_km2 | Cloud Run (compute) | engines/hydrology.py | NumPy | Library | Compliant | N/A | P0 | Wed 14 | C20 | Not started
C22 | S2 | Streams, reaches, catchments | upa ≥ 5 km² streams; split at confluences / 2 km; drain_cell tracing | upa, downstream | reach table, catch_reach | Cloud Run (compute) | engines/hydrology.py | NumPy | Library | Compliant | N/A | P0 | Thu 15 | C21 | Not started
C23 | S2 | Synthetic rating curves | HAND + Manning per reach (Zheng et al. 2018) | hnd, reaches, n | Q(h) tables | Cloud Run (compute) | engines/hydrology.py | NumPy | Library | Compliant | N/A | P0 | Thu 15 | C22 | Not started
C24 | S2 | Convergence hotspots | Confluences + upa surges | Streams | Hotspots H1… | Cloud Run (compute) | engines/hydrology.py | — | — | Compliant | N/A | P1 | Thu 15 | C22 | Not started
C25 | S3 | M1 stage-only flood map | depth = max(0, stage − HAND); mask permanent water | hand, gsw_occ | depth grid | Cloud Run (compute) | engines/flood.py | — | — | Compliant | N/A | P0 | Wed 14 | C09 | Not started
C26 | S3 | Runoff coefficient | Dynamic World class → C table (editable) | lc_class | C per reach | Cloud Run (compute) | engines/rainfall.py | — | — | Compliant | N/A | P0 | Thu 15 | C10 | Not started
C27 | S3 | Rational method runoff | Q = 0.278·C·i·A (m³/s) | C, i (mm/h), A_local (km²) | Q per reach per hour | Cloud Run (compute) | engines/rainfall.py | — | — | Compliant | N/A | P0 | Thu 15 | C26, C21 | Not started
C28 | S3 | Time of concentration | Kirpich tc; flow length by Hack's law | A_local, reach slope | tc per reach | Cloud Run (compute) | engines/rainfall.py | — | — | Compliant | N/A | P0 | Thu 15 | C22 | Not started
C29 | S3 | Hourly worst-case envelope | Window-mean intensity, rising ramp, SRC inversion, non-decreasing stage, per-reach depth | Rain series, SRC | depth_stack [H], stage per reach, flooded km² | Cloud Run (compute); Cloud Storage | engines/flood.py; runs/{id}/depth.npz | — | — | Compliant | N/A | P0 | Thu 15 | C23, C27, C28 | Not started
C30 | S4 | AHP weights module | Principal eigenvector; CI, CR; reject CR ≥ 0.10 | Pairwise matrix | Weights, CR | Cloud Run (compute) | engines/ahp.py | NumPy | Library | Compliant | N/A | P1 | Thu 15 | — | Not started
C31 | S4 | Flood susceptibility index (FSI) | Weighted sum of 7 normalised factors; 5 classes | hand, gfd/gsw, dist_stream, upa, rain_clim, slope, C | fsi + PNG | Cloud Run (compute) | engines/fsi.py | — | — | Compliant | N/A | P1 | Thu 15 | C30, C08–C14 | Not started
C32 | S5 | Landslide factor classes | Binned slope, rain, NDVI, distances, clay, curvature, aspect | Layers | Class rasters | Cloud Run (compute) | engines/landslide.py | — | — | Compliant | N/A | P1 | Thu 15 | C08–C13, C17 | Not started
C33 | S5 | Frequency Ratio from past landslides | FR per class in 50 km training box; fallback to expert ratings if < 15 points | Classes, inventory | Class ratings | Earth Engine (noncommercial) | projects/sat-io/open-datasets/events/global_landslide_1970-2019 (community catalog, VERIFY licence) | NASA GLC data (community-hosted in EE) | Open public data hosted in Earth Engine | Compliant | N/A | P1 | Thu 15 | C32 | Not started
C34 | S5 | Static landslide susceptibility | LSI = Σ AHP weight × class rating; quantile classes | Ratings, weights | lsi_static + PNG | Cloud Run (compute) | engines/landslide.py | — | — | Compliant | N/A | P1 | Thu 15 | C30, C33 | Not started
C35 | S5 | Rainfall-modulated landslide classes | Caine (1980) threshold ratio g ∈ [0.5, 1.5] | lsi_static, rain series | lsi_dyn_class [H] | Cloud Run (compute) | engines/landslide.py | — | — | Compliant | N/A | P1 | Thu 15 | C34 | Not started
C36 | S6 | Proxy structure classification | Rules on footprint, height, density, new-since-2016; fragility + confidence | Open Buildings | Class per building | Cloud Run (compute) | engines/buildings.py | SciPy KD-tree | Library | Compliant | Replaces Street View classification (§3.2.3(a),(c)(v)) | P0 | Thu 15 | C16 | Not started
C37 | S6 | Population to buildings | Volume-weighted share per 30 m cell; multiplier/override | pop30, buildings | pop per building + unattributed | Cloud Run (compute) | engines/population.py | — | — | Compliant | N/A | P0 | Thu 15 | C15, C36 | Not started
C38 | S6 | Exposure and triage | Depth/landslide per building per hour; risk score; clusters | depth_stack, lsi_dyn, pop | ExposureSummary, triage | Cloud Run (compute) | engines/exposure.py | — | — | Compliant | N/A | P0 | Thu 15 | C29, C35, C37 | Not started
C39 | S6 | Field verification queue | risk × (1 − confidence) × people; top 50 | Exposure, classes | Queue V1… | Cloud Run (compute) | engines/exposure.py | — | — | Compliant | N/A | P1 | Thu 15 | C38 | Not started
C40 | S7 | Road graph projection and edge sampling | Project to UTM; sample every 30 m; bridge flag | OSM graphs | edge_cells, bridge | Cloud Run (compute) | engines/roads.py | OSMnx, NetworkX | Libraries + open data | Compliant (open data) | N/A | P0 | Fri 16 | C17, C07 | Not started
C41 | S7 | Travel time | Tobler hiking function (walk); OSMnx speeds (drive) | Edges, DEM | t0_s per edge | Cloud Run (compute) | engines/roads.py | OSMnx | Library | Compliant | N/A | P0 | Fri 16 | C40, C08 | Not started
C42 | S7 | Shelters and capacity | OSM amenities; footprint × floors × 0.6 / 3.5 m² (Sphere) | POIs, buildings | Shelters S1… | Cloud Run (compute) | engines/shelters.py | OpenStreetMap POIs | Open data; Places API lat/lng can't be used for analysis | Compliant (open data) | Avoids §3.2.3(c)(iv) | P0 | Fri 16 | C17, C16 | Not started
C43 | S7 | Assembly and staging points | Dry, flat, low-landslide components near roads | depth, hand, slope, lsi | A1…, G1… | Cloud Run (compute) | engines/shelters.py | SciPy ndimage | Library | Compliant | N/A | P1 | Fri 16 | C29, C34 | Not started
C44 | S8 | Edge closure by hour | Flood depth limit, bridge cut stage, landslide class 5, user blocks | depth_stack, lsi_dyn, polygons | first_closed_hour + reason | Cloud Run (compute) | engines/routing.py | Shapely | Library | Compliant | N/A | P0 | Fri 16 | C40, C29, C35 | Not started
C45 | S8 | Capacity-aware assignment | Transportation problem via network simplex; overflow edge | Demand nodes, shelters, travel times | Allocations, capacity gap | Cloud Run (compute) | engines/routing.py | NetworkX | Library | Compliant | N/A | P0 | Fri 16 | C44, C42, C38 | Not started
C46 | S8 | Routes and passable-until | Shortest paths; min closure hour; use-now flag | Allocations | Routes GeoJSON, bridges table | Cloud Run (compute); Cloud Storage | engines/routing.py | NetworkX | Library | Compliant | Drawn on Google map as our overlay (allowed) | P0 | Fri 16 | C45 | Not started
C47 | S9 | Crowding / evacuation-difficulty index | POI attractor weights + building density + road narrowness | OSM POIs, buildings, edges | crowd grid, crowd_e, hotspots X1… | Cloud Run (compute) | engines/crowding.py | OpenStreetMap POIs | Open data | Compliant (open data) | Replaces Places busyness and Street View congestion (§3.2.3(c)(iv),(v)) | P1 | Fri 16 | C17, C16 | Not started
C48 | S9 | Live traffic (visual only) | Toggle the Maps Traffic Layer for humans | — | Map layer | Google Maps Platform | Maps JavaScript API TrafficLayer | — | — | Compliant | Display only, never read into the engine | P2 | Fri 16 | C71 | Not started
C49 | S10 | Forecast (hourly/daily/alerts) | forecast/hours (240 h), forecast/days (10 d), publicAlerts | AOI centroid | Rain series, alerts | Google Maps Platform | Weather API (weather.googleapis.com/v1/...) | — | — | Compliant | 10-min in-memory only; VERIFY Weather caching terms | P1 | Fri 16 | C03 | Not started
C50 | S10 | IMD adapter (optional) | Same interface as Weather provider | AOI | Rain series | — | — | IMD data (Govt of India) | Optional official source; default stays Google | Optional non-Google, flag in pitch | N/A | P2 | Fri 16 | C49 | Not started
C51 | S10 | Scenario series builders | Wettest window; worst/best multipliers; manual hyetographs | Forecast, params | rain_series + label | Cloud Run (compute) | engines/rainfall.py | — | — | Compliant | N/A | P1 | Fri 16 | C49 | Not started
C52 | S10 | Past 90 days rainfall | Daily sums of half-hourly IMERG | AOI centroid | Chart series | Earth Engine (noncommercial) | NASA/GPM_L3/IMERG_V07 precipitation | — | — | Compliant | N/A | P1 | Fri 16 | C07 | Not started
C53 | S10 | Historical extreme scenario | Max daily CHIRPS 2001–2024 near the AOI | AOI | Daily total (mm) | Earth Engine (noncommercial) | UCSB-CHG/CHIRPS/DAILY | — | — | Compliant | N/A | P1 | Fri 16 | C13 | Not started
C54 | S11 | India flood heat map | GFD event count tiles via getMapId | — | Tile URL | Earth Engine (noncommercial) | GLOBAL_FLOOD_DB/MODIS_EVENTS/V1 | — | — | Compliant | EE tiles overlaid on Maps (allowed) | P1 | Sat 17 | C01 | Not started
C55 | S11 | Landslide heat map | GLC points → GeoJSON heat | — | Points | Earth Engine (noncommercial) | projects/sat-io/open-datasets/events/global_landslide_1970-2019 | NASA GLC | Open data in EE | Compliant | N/A | P1 | Sat 17 | C01 | Not started
C56 | S11 | AOI historical event table | Events with flooded pixels in AOI + GLC points | AOI | Event list | Earth Engine (noncommercial) | GFD properties (VERIFY names) | — | — | Compliant | N/A | P1 | Sat 17 | C14 | Not started
C57 | S11 | Grounded web incidents | Historian agent with built-in google_search; JSON with sources | Place, bbox | Incidents with URLs | Vertex AI (Gemini); ADK; Grounding with Google Search; Geocoding API | ADK google_search tool; Geocoding for display markers | — | — | Compliant (Gemini) | Show grounding attribution (VERIFY); geocodes for display only | P2 | Sat 17 | C65 | Not started
C58 | S11 | History–model agreement badge | % of GFD flooded cells inside FSI ≥ 0.6 | gfd, fsi | Badge value | Cloud Run (compute) | engines/fsi.py | — | — | Compliant | N/A | P2 | Sat 17 | C31, C14 | Not started
C59 | S12 | Photo upload | Multipart upload; EXIF GPS or map pin | Image | GCS object + doc | Cloud Storage; Firestore | photos/{aoi_id}/{photo_id}.jpg | Pillow | Library | Compliant | User's own photos, not Maps content | P1 | Sat 17 | C01 | Not started
C60 | S12 | Gemini vision classification | Structured output: building class/materials or drain condition + confidence | Photo | BuildingPhotoResult / DrainPhotoResult | Vertex AI (Gemini Flash) | google-genai generate_content with response_schema | — | — | Compliant (Gemini) | Compliant (no Street View/Maps imagery) | P1 | Sat 17 | C59 | Not started
C61 | S13 | Urban pluvial ponding screening | Priority-flood fill; depression volume vs rain excess | DEM, C, rain | Ponding likelihood | Cloud Run (compute) | engines/pluvial.py | NumPy/heapq | Library | Compliant | N/A | P2 | Sat 17 | C08 | Not started
C62 | S13 | Drain inspection priority | Waterways/culverts/road crossings scored by accumulation, FSI/ponding, exposure | OSM waterways, layers | Drains D1… | Cloud Run (compute) | engines/drains.py | OpenStreetMap waterways | Open data | Compliant (open data) | N/A | P2 | Sat 17 | C17, C61 | Not started
C63 | S14 | Deterministic run pipeline | Fixed order S10→S3→S5→S6→S7.7→S8→render→store | ScenarioParams | RunResult | Cloud Run; Firestore; Cloud Storage | pipeline/run_pipeline.py | — | — | Compliant | N/A | P0 | Sat 17 | C29–C46 | Not started
C64 | S14 | Agent tools | Typed Python functions returning compact dicts | Run ids, params | Tool results | Agent Development Kit (ADK) | ADK FunctionTool (auto-wrapped) | — | — | Compliant (Google agent platform) | N/A | P0 | Sat 17 | C63 | Not started
C65 | S14 | Scenario planner agent | NL → ScenarioParams via output_schema; human approves diff | Text, current params | ScenarioParams | Vertex AI (Gemini Flash); ADK | ADK LlmAgent(output_schema=ScenarioParams) | — | — | Compliant (Gemini) | N/A | P0 | Sat 17 | C64 | Not started
C66 | S14 | Analyst chat agent | Tool-calling what-if assistant; cites ids; never invents numbers | Chat message | Reply + new run id | Vertex AI (Gemini Flash); ADK | ADK LlmAgent + Runner + InMemorySessionService | — | — | Compliant (Gemini) | N/A | P1 | Sat 17 | C64 | Not started
C67 | S14 | Full-assessment workflow (showcase) | SequentialAgent: planner → pipeline agent → advisor | Text | Run + advisory | ADK | ADK SequentialAgent + custom BaseAgent | — | — | Compliant (Google agent platform) | N/A | P2 | Sat 17 | C65, C69 | Not started
C68 | S15 | Facts builder | Deterministic compact JSON with ids (K, C, S, B, R, A, G, M, H, L, X, D, V) | RunResult | facts JSON | Cloud Run (compute) | pipeline/facts.py | — | — | Compliant | N/A | P0 | Sat 17 | C63 | Not started
C69 | S15 | Advisory generation | Three horizons, P1–P3, evidence ids, exact disclaimer | facts JSON | Advisory | Vertex AI (Gemini Pro) | google-genai response_schema=Advisory | — | — | Compliant (Gemini) | N/A | P0 | Sat 17 | C68 | Not started
C70 | S15 | Advisory validator and rules fallback | Drop unknown ids / unsupported numbers; rule templates fill gaps | Advisory, facts | Validated Advisory | Cloud Run (compute); Firestore | agents/advisor.py; advisories/{id} | — | — | Compliant | N/A | P0 | Sat 17 | C69 | Not started
C71 | S16 | Base map and overlays | Map with Map ID; deck.gl GoogleMapsOverlay for bitmaps/GeoJSON/heat | URLs, GeoJSON | Interactive map | Google Maps Platform | Maps JavaScript API via @vis.gl/react-google-maps | deck.gl (open-source) | Library | Compliant | Our data drawn over Maps (allowed) | P0 | Wed 14 | C02 | Not started
C72 | S16 | AOI and block-road drawing | Rectangle and polygon tools | User input | GeoJSON | Google Maps Platform | Terra Draw + Google Maps adapter (Drawing Library unavailable since May 2026) | Terra Draw (open-source) | Library; Google points to it as the replacement | Compliant | N/A | P0 | Wed 14 | C71 | Not started
C73 | S16 | Explore page | India history heat, search, draw → prepare | — | AOI | Google Maps Platform; Earth Engine tiles | Maps JS; EE getMapId tiles | — | — | Compliant | Display only | P0 | Wed 14 | C71, C72, C54 | Not started
C74 | S16 | Workspace page | Layers, scenario controls, time slider, results, charts | RunResult | UI | Google Maps Platform | Maps JS | Recharts (open-source) | Library | Compliant | Display only | P0 | Fri 16 | C63 | Not started
C75 | S16 | Advisory page + print | Three-horizon cards, evidence fly-to, print CSS | Advisory | Brief / PDF via browser print | Firebase Hosting | — | — | — | Compliant | N/A | P0 | Sat 17 | C70 | Not started
C76 | S16 | Verify page | Verification queue + photo uploader | Queue, photos | Results | Firebase Hosting | — | — | — | Compliant | N/A | P1 | Sat 17 | C39, C60 | Not started
C77 | S16 | Methods and attributions page | Methods, formulas, AHP tables, limitations, licences | — | Page | Firebase Hosting | — | — | — | Compliant | Attributions shown | P0 | Sat 17 | — | Not started
C78 | S16 | Chat panel | Slide-over chat; loads new runs | Chat | UI | Firebase Hosting; Cloud Run | /api/chat | — | — | Compliant | N/A | P1 | Sat 17 | C66 | Not started
C79 | S16 | Place search box | Backend geocoding of a typed place | Text | Map centre | Google Maps Platform | Geocoding API (server key) | — | — | Compliant | Display/navigation only | P1 | Wed 14 | C03 | Not started
C80 | S16 | Street View viewing | Pegman for humans to look; never sent to Gemini or stored | — | Panorama | Google Maps Platform | Maps JavaScript API Street View | — | — | Compliant | Display only (§3.2.3 respected) | P2 | Sat 17 | C71 | Not started
C81 | S17 | Deploy and smoke test | Deploy both; health → prepare → run → advisory | — | Live URLs | Cloud Run; Firebase Hosting; Secret Manager | gcloud run deploy; firebase deploy | — | — | Compliant (required hosting) | Keys restricted | P0 | Sat 17 | All P0 | Not started
C82 | S18 | Demo AOI preprocessing and backtest | Prepare Rudraprayag + Mumbai; overlap vs GFD | AOIs | Cached layers; backtest % | Earth Engine (noncommercial); Cloud Run | scripts/preprocess_demo_aoi.py | — | — | Compliant | N/A | P0 | Sun 18 | C81 | Not started
C83 | S18 | Submission assets | README, architecture diagram, demo video, format per Hack2skill | — | Submission | — | — | — | — | Check dashboard | N/A | P0 | Sun 18 | C82 | Not started
C84 | S19 | 3D terrain + buildings + water (OPT) | deck.gl TerrainLayer from our DEM; extruded Open Buildings; water at dem + depth | DEM, buildings, depth | 3D view | Earth Engine data; Firebase Hosting | deck.gl Deck (standalone) | deck.gl (open-source) | Library | Compliant | Elevation API NOT used for terrain (§3.2.3(c)(iii)) | OPT | Sun 18 | C29, C16 | Not started
C85 | S19 | Photorealistic 3D backdrop (OPT) | 3D Maps where coverage exists | — | 3D backdrop | Google Maps Platform | Map Tiles API / Maps JS 3D Maps (VERIFY API, coverage) | — | — | Compliant | Display only | OPT | Sun 18 | C84 | Not started

## Google services
Google service | Used for | Component IDs | Billing / credit | Spec section | Notes
Cloud Run | Backend API + all engine compute + ADK agents | C01, C06–C70, C81 | Trial credit ($300, 90 days) | S0.12, S17.1 | Required host by challenge rules. Region asia-south1.
Firebase Hosting | Frontend web app; /api rewrite to Cloud Run | C02, C71–C80 | Free tier / trial credit | S0.13, S17.2 | Required host option by challenge rules.
Vertex AI: Gemini (Flash) | Scenario planner, analyst chat, photo classifier, historian | C05, C57, C60, C65, C66 | Trial credit | S0.10, S14.8 | Model name picked from the live model list. Never hardcoded.
Vertex AI: Gemini (Pro) | Advisory brief (structured output) | C69 | Trial credit | S15.2 | Structured output with response_schema.
Agent Development Kit (ADK) | Agents, function tools, runner, sessions, SequentialAgent | C64–C67, C57 | Open-source framework (runs on Cloud Run) | S14 | Google's agent platform, matching the challenge's 'agentic' track.
Grounding with Google Search | Historian agent finds documented past incidents with sources | C57 | Billed per grounded request (VERIFY price) | S11.4 | Show grounding attributions as required (VERIFY).
Earth Engine | All geospatial analysis data: DEM, HAND, land cover, population, buildings, rainfall, floods, landslides; map tiles | C08–C16, C20, C33, C52–C56, C82, C84 | Noncommercial: not charged; quota 150–1,000 EECU-h/month | S0.3, S1, S2 | Register the project as noncommercial. Some datasets are CC-BY-NC.
Cloud Storage | Layer cache (.npz), overlay PNGs, run arrays, photos | C17–C19, C29, C46, C59 | Trial credit | S0.5, S1.11 | Private bucket; signed URLs.
Firestore | AOIs, runs, advisories, photo results, history cache | C06, C18, C59, C63, C70 | Free tier / trial credit | S0.5 | Native mode, asia-south1.
Secret Manager | Server API key | C03 | Trial credit | S0.6 | Mounted as an env var on Cloud Run.
Cloud Build + Artifact Registry | Container builds for Cloud Run | C01, C81 | Trial credit | S0.12 | gcloud run deploy --source.
Cloud Billing budgets | Spend alerts | C04 | Free | S0.8 | $100 budget with alerts.
IAM | Service account pravah-backend with least-privilege roles | C03 | Free | S0.4 | Roles: Vertex AI User, EE role (VERIFY), Datastore User, Storage (bucket), Secret Accessor, Service Usage Consumer.
Maps JavaScript API | Base map, our overlays, Traffic Layer, Street View viewing | C48, C71–C74, C80 | Maps monthly free usage + trial credit if on the same billing account (VERIFY) | S0.6–S0.7, S16 | Display only. Never an analysis input.
Weather API (Maps Platform) | Hourly (240 h) and daily (10 d) forecasts, public alerts | C49 | Maps free usage + trial credit (VERIFY) | S10.2 | No persistent caching (§3.2.3(b)); VERIFY service-specific terms.
Geocoding API (Maps Platform) | Search box; display markers for web incidents | C57, C79 | Maps free usage + trial credit | S11.4, S16.3 | Display and navigation only.
Map Tiles API (Maps Platform) | Photorealistic 3D backdrop (optional) | C85 | Maps free usage + trial credit | S19.2 | Optional; VERIFY coverage over the demo AOI.

## Data sources
Dataset | Provider | Access ID / endpoint | Resolution | Period | Licence | Used in | ID check
Copernicus DEM GLO-30 | ESA / Copernicus | Earth Engine: COPERNICUS/DEM/GLO30 (marked deprecated; successor COPERNICUS/DEM/GLO30_2024_1) | 30 m | — | Free licence (except Armenia/Azerbaijan) | C08, C84 | Verified 14 Oct (successor ID: VERIFY)
MERIT Hydro v1.0.1 (hnd, dir, upa, elv) | Yamazaki et al. | Earth Engine: MERIT/Hydro/v1_0_1 | ~90 m (3″) | — | CC-BY-NC 4.0 or ODbL 1.0 | C09, C20–C23 | Verified 14 Oct
Open Buildings v3 polygons | Google Research | Earth Engine: GOOGLE/Research/open-buildings/v3/polygons | Vector | — | CC-BY 4.0 | C16, C36 | Verified 14 Oct (India coverage: check count)
Open Buildings 2.5D Temporal | Google Research | Earth Engine: GOOGLE/Research/open-buildings-temporal/v1 | 4 m effective | 2016–2023 | CC-BY 4.0 or ODbL | C16, C36, C84 | Verified 14 Oct
WorldPop population | WorldPop | Earth Engine: WorldPop/GP/100m/pop | 100 m | Latest year: VERIFY | VERIFY (typically CC-BY 4.0) | C15, C37 | ID verified 14 Oct
Global Flood Database v1 | Cloud to Street / Tellman et al. | Earth Engine: GLOBAL_FLOOD_DB/MODIS_EVENTS/V1 | 250 m classification | 2000–2018 | CC-BY-NC 4.0 | C14, C54, C56, C58 | Verified 14 Oct
CHIRPS daily rainfall | UCSB Climate Hazards Center | Earth Engine: UCSB-CHG/CHIRPS/DAILY | 0.05° | 1981 → ~2026 | VERIFY | C13, C53 | Verified 14 Oct
GPM IMERG V07 | NASA | Earth Engine: NASA/GPM_L3/IMERG_V07 | 0.1°, half-hourly (mm/h) | 1998 → near real time | NASA open data | C52 | Verified 14 Oct
Dynamic World land cover | Google / WRI | Earth Engine: GOOGLE/DYNAMICWORLD/V1 | 10 m | 2015 → present | VERIFY (CC-BY 4.0) | C10, C26 | VERIFY
Sentinel-2 SR (harmonized) | ESA / Copernicus | Earth Engine: COPERNICUS/S2_SR_HARMONIZED | 10 m | 2017 → present | Copernicus open licence | C11 | VERIFY
JRC Global Surface Water | EC JRC | Earth Engine: JRC/GSW1_4/GlobalSurfaceWater (VERIFY latest) | 30 m | 1984 → ~2021 | VERIFY | C14 | VERIFY
OpenLandMap soil clay | OpenLandMap | Earth Engine: OpenLandMap/SOL/SOL_CLAY-WFRACTION_USDA-3A1A1A_M/v02 (VERIFY) | 250 m | — | VERIFY | C12 | VERIFY
NASA Global Landslide Catalog | NASA GSFC (community-hosted) | Earth Engine community: projects/sat-io/open-datasets/events/global_landslide_1970-2019 | Points | 1970–2019 | Public access (VERIFY formal terms) | C33, C55 | Listed in community catalog 14 Oct
OpenStreetMap roads, POIs, waterways | OSM contributors | OSMnx → Overpass API | Vector | Live | ODbL ('© OpenStreetMap contributors') | C17, C40–C47, C62 | Open data
Weather forecast | Google Maps Platform | Weather API: forecast/hours, forecast/days, publicAlerts | Point | 240 h / 10 d | Maps Platform Terms | C49 | Endpoints verified 14 Oct
Field photos | Authorities / project owner | User upload | Photo | — | Owner's own images or openly licensed with attribution | C59, C60 | —

## Compliance
Area | Rule | Source | How we comply | Open risk / action
Challenge | Use Google AI models (Gemini/Gemma) or Google agentic platforms | Event listing (Metropolis, Hack2skill) | Gemini on Vertex AI for every AI step; agents built with ADK | None
Challenge | Deploy on Google Cloud via Cloud Run or Firebase | Event listing | Backend on Cloud Run; frontend on Firebase Hosting | None
Challenge | Team of 2–4, all 21+ | Event listings | Confirm the second member has joined on the dashboard | Team card showed an empty slot
Challenge | Prototype due 18 Oct 2026 | Hack2skill dashboard | Submit by 12:00 IST Sunday | Check the required submission format
Maps ToS §3.2.3(a) | No scraping, bulk download of Street View images or elevation values | cloud.google.com/maps-platform/terms | No Street View/elevation extraction; analysis data from Earth Engine + OSM | None
Maps ToS §3.2.3(b) | No caching except as permitted | Same | Weather responses held in memory 10 min; runs store the scenario label + series used | VERIFY Weather API service-specific caching terms
Maps ToS §3.2.3(c)(iii) | No terrain models from Elevation API values | Same | Terrain/slope/HAND from Copernicus DEM + MERIT in Earth Engine; Elevation API not used | None
Maps ToS §3.2.3(c)(iv) | No Places API lat/lng in point-in-polygon analysis | Same | Shelters, POIs and crowding from OpenStreetMap | None
Maps ToS §3.2.3(c)(v) | No indexes built from Street View imagery | Same | Building/drain classification from authorities' own field photos; Street View is human viewing only | Changed from the earlier plan; explain in the pitch
Maps ToS §3.2.3(c)(vii) | No Maps content to train/test/fine-tune AI | Same | No Maps content goes to Gemini | None
Earth Engine | Noncommercial registration and quota | developers.google.com/earth-engine/guides/noncommercial_tiers | Register as noncommercial research prototype; monitor EECU use | Commercial use later needs a commercial EE plan
Dataset licences | CC-BY-NC (MERIT Hydro, GFD); CC-BY (Open Buildings); ODbL (OSM) | Dataset pages | Attributions on the Methods page and footer; non-commercial prototype | Replace or licence before any commercial use
Grounding with Google Search | Display requirements for grounded answers | Gemini grounding terms | Show sources and search attribution in the history panel | VERIFY exact display requirements
Safety framing | Decision-support only, never prediction or an order | Project decision | Exact disclaimer on every results surface; wording rules | None
Privacy | No personal data; no inference about people | Project decision | Photos are of structures/drains only; avoid faces; classify structures, never people | Demo photos must be the owner's own or openly licensed

## Day plan
Day | Stages | Checkpoint | Components planned | Components done | % done
Wed 14 Oct | S0, S1, S2, S3-M1 | Draw an AOI → layers prepared → flood depth from a stage slider on the Google map (deployed) | 26 | 0 | 0%
Thu 15 Oct | S3 M2–M4, S4, S5, S6 | Rain scenario → hourly flood + landslide susceptibility + exposure numbers | 17 | 0 | 0%
Fri 16 Oct | S7, S8, S9, S10, S16 Workspace | Full what-if loop: close shelter / block road → reroute, capacity gap | 15 | 0 | 0%
Sat 17 Oct | S14, S15, S11, S12, S13, S16 pages, S17 | Advisory + chat + history + photo verify, deployed | 23 | 0 | 0%
Sun 18 Oct | S18 (+ S19 only if all green) | Submitted by 12:00 IST | 4 | 0 | 0%

## Progress
Stage | Components | Done | In progress | Blocked | % done
S0 | 5 | 0 | 0 | 0 | 0%
S1 | 14 | 0 | 0 | 0 | 0%
S2 | 5 | 0 | 0 | 0 | 0%
S3 | 5 | 0 | 0 | 0 | 0%
S4 | 2 | 0 | 0 | 0 | 0%
S5 | 4 | 0 | 0 | 0 | 0%
S6 | 4 | 0 | 0 | 0 | 0%
S7 | 4 | 0 | 0 | 0 | 0%
S8 | 3 | 0 | 0 | 0 | 0%
S9 | 2 | 0 | 0 | 0 | 0%
S10 | 5 | 0 | 0 | 0 | 0%
S11 | 5 | 0 | 0 | 0 | 0%
S12 | 2 | 0 | 0 | 0 | 0%
S13 | 2 | 0 | 0 | 0 | 0%
S14 | 5 | 0 | 0 | 0 | 0%
S15 | 3 | 0 | 0 | 0 | 0%
S16 | 10 | 0 | 0 | 0 | 0%
S17 | 1 | 0 | 0 | 0 | 0%
S18 | 2 | 0 | 0 | 0 | 0%
S19 | 2 | 0 | 0 | 0 | 0%
Total | 85 | 0 | 0 | 0 | 0%
P0 components done | 0 / 48